## Cover
Ironbridge Industrial Group — Digital transformation model
Armageddon 2026 case submission support. Team ID: [to be added]. USD million unless stated; baseline FY2025; mandate Jan-2026 to Jun-2027. Plan shown at the base-case realisation factor (Assumptions).
Win condition — is Ironbridge "turned around" by Jun-27?
Test | Unit | Target | Plan | Result | Why this test
1 Liquidity: new money needed beyond rollover + identified sources | USD m | 0 | -10.9755 | MET | Mandate is funded without fresh money (momentum needs it)
2 Solvency: exit interest cover, downside case (50% realisation) | x | 1 | 1.1128 | MET | Earnings cover interest even if only half the benefits land
3 Auto: run-rate EBITDA vs its share of maintenance capex | USD m | 20.4545 | 28.6867 | MET | Auto funds its own upkeep → no longer a cash drain, so no case for a forced sale
4 Digital: net digital contribution (run-rate) | USD m | 0 | 8.7285 | MET | Digital pays for itself
Key outputs
| Unit | Base (momentum) | Plan | Δ | Note
EBITDA 2025A | USD m | 25
EBITDA — Jun-27 run-rate | USD m | 48 | 68.7285 | 20.7285 | Base includes the automatic roll-off of 23 of 2025 implementation costs (Ex.6)
EBITDA margin — Jun-27 run-rate | % | 4.034% | 5.735% | 1.702%
EBITDA — last twelve months to Jun-27 | USD m | 45 | 49.1169 | 4.1169 | What lenders test
Free cash flow — 18 months | USD m | -141.734 | -74.0245 | 67.7095 | Before disposals and financing
Net debt — Jun-27 | USD m | 896.734 | 829.0245 | -67.7095 | 2025: 755
Net debt / LTM EBITDA — Jun-27 | x | 19.9274 | 16.8786 | -3.0488 | 2025: 30.2x
Interest cover — LTM to Jun-27 | x | 0.89572 | 1.008 | 0.11226 | 2025: 0.6x
Interest cover — Jun-27 run-rate | x | 0.80568 | 1.2752 | 0.46948
New money to raise (after rollover and identified sources) | USD m | 56.734 | -10.9755 | -67.7095 | Sources & uses on Projection
Run-rate EBITDA vs free-cash-flow break-even | USD m | -91.5771 | -50.1697 | 41.4074 | Negative: balance-sheet action needed beyond Jun-27
Auto EBITDA margin — Jun-27 run-rate (plan) | % |  | 5.014% |  | 2025: 0.9%
Net digital contribution — 2025 vs Jun-27 run-rate (plan) | USD m | -35 | 8.7285 | 43.7285 | Column C here = 2025 actual, not base
Run-rate EBITDA at 100% realisation (stretch) / 50% (downside) | USD m | 77.4797 | 59.9773 |  | C = stretch, D = downside
Integrity checks (all should read OK)
Check |  | Value | Status
Balance sheet balances (2022–25) |  | 0 | OK
Rebuilt EBITDA = case-reported (2022–25) |  | 0 | OK
Rebuilt net income = case-reported (2022–25) |  | 0 | OK
Opex breakdown = case total (2022–25) |  | 0 | OK
Segments reconcile to Group revenue & EBITDA |  | 0 | OK
Cash-flow closing cash = balance sheet (2023–25) |  | 0 | OK
Debt raised = change in total debt (2023–25) |  | 0 | OK
D&A split = total D&A (2023–25) |  | 0 | OK
Working-capital change = cash-flow line (2023–25) |  | 0 | OK
Ex.6 cost breakdown = Ex.5 operating cost |  | 0 | OK
Project + central digital opex = Ex.1 digital opex |  | 0 | OK
EBITDA bridge 2022→25 closes |  | 0 | OK
Initiative segment splits sum to 100% |  | 0 | OK
Workstream view = initiative total |  | 0 | OK
Segment run-rates sum to Group run-rate |  | 0 | OK
Sources = uses (plan) |  | 0 | OK
Zero cash tax valid: highest projected PBT |  | -43.7671 | OK |  | Must be negative
How to read this workbook
Blue text |  | Input typed from the case or an assumption
Black text |  | Formula
Green text |  | Direct link to another sheet
Yellow fill |  | Key driver or headline output
Sheet guide
Case_Financials |  | Exhibits 1–4 typed in, subtotals rebuilt and reconciled
Case_Digital |  | Exhibits 5–7: programme economics, cost breakdown, KPIs
Case_Ops |  | Exhibit 8: footprint, energy, labour, digital readiness
Diagnosis |  | Ratios, EBITDA bridge, programme scorecard, Auto digital burden, consistency flag
Assumptions |  | Every judgement call with rationale, benchmark, funding bridge and win-condition targets
Initiatives |  | Run-rate economics, overlap netting, phasing, workstreams, segment split, working capital
Projection |  | Base vs plan EBITDA, cash, net debt, lender (LTM) view, sources & uses
Segments |  | Jun-27 run-rate by business, SMC break-even price, SMC exit case
Sensitivity |  | Realisation scenarios and one-at-a-time shocks
Sources |  | External benchmarks with URLs

## Case_Financials
Case data — financial exhibits (USD m; FY ends 31 Dec)
Blue = typed from the case exhibits. Black = formulas that rebuild case subtotals; "case-reported" rows are kept to prove the rebuild matches.
Exhibit 1 — Income statement
USD m | 2022 | 2023 | 2024 | 2025 | Source / note
Revenue | 1150 | 1205 | 1230 | 1190 | Ex.1
Cost of sales (excl. D&A) | 860 | 910 | 945 | 930 | Ex.1. Includes energy and direct production labour (Ex.8) and the 2025 digital gross benefits (Ex.5)
Gross profit | 290 | 295 | 285 | 260
Operating expenses excl. D&A | 168 | 187 | 215 | 235 | Sum of the Ex.1 opex breakdown below
EBITDA | 122 | 108 | 70 | 25
Depreciation & amortisation | 58 | 66 | 78 | 90 | Ex.1
EBIT | 64 | 42 | -8 | -65
Net finance costs | 24 | 27 | 33 | 40 | Ex.1 — interest on debt, net
Profit before tax | 40 | 15 | -41 | -105
Tax | 10 | 4 | 0 | 0 | Ex.1 (2023 rounded to 4 per case footnote)
Net income | 30 | 11 | -41 | -105
EBITDA — case-reported | 122 | 108 | 70 | 25 | Ex.1, for reconciliation
Net income — case-reported | 30 | 11 | -41 | -105 | Ex.1, for reconciliation
Exhibit 1 — Operating expense breakdown
USD m | 2022 | 2023 | 2024 | 2025
Non-digital personnel costs | 90 | 95 | 101 | 108 | Ex.1
Selling and customer support | 35 | 38 | 42 | 45 | Ex.1
Digital and AI operating costs | 8 | 18 | 35 | 48 | Ex.1 — expensed digital personnel, software, cloud, support, implementation
Other overheads | 35 | 36 | 37 | 34 | Ex.1
Total operating expenses — case-reported | 168 | 187 | 215 | 235 | Ex.1, for reconciliation
Exhibit 2 — Balance sheet
USD m | 2022 | 2023 | 2024 | 2025
Cash & cash equivalents | 90 | 75 | 55 | 30 | Ex.2
Trade receivables | 150 | 158 | 168 | 172 | Ex.2
Inventory | 205 | 220 | 240 | 255 | Ex.2
Other current assets | 38 | 40 | 43 | 45 | Ex.2
Total current assets | 483 | 493 | 506 | 502
PPE (net) | 590 | 630 | 660 | 680 | Ex.2
Capitalised digital & AI assets | 65 | 100 | 135 | 155 | Ex.2 — net carrying value; 65 opening balance = earlier systems
Other intangible assets | 192 | 191 | 159 | 113 | Ex.2
Total non-current assets | 847 | 921 | 954 | 948
TOTAL ASSETS | 1330 | 1414 | 1460 | 1450
Trade payables | 165 | 178 | 188 | 195 | Ex.2
Short-term debt | 90 | 115 | 145 | 180 | Ex.2
Other current liabilities | 55 | 58 | 60 | 63 | Ex.2
Total current liabilities | 310 | 351 | 393 | 438
Long-term debt | 470 | 510 | 555 | 605 | Ex.2
Other long-term liabilities | 30 | 30 | 30 | 30 | Ex.2
Total non-current liabilities | 500 | 540 | 585 | 635
Total liabilities | 810 | 891 | 978 | 1073
Equity | 520 | 523 | 482 | 377 | Ex.2
TOTAL LIABILITIES & EQUITY | 1330 | 1414 | 1460 | 1450
Check: assets − liabilities & equity (should be 0) | 0 | 0 | 0 | 0
Exhibit 3 — Segment financials
USD m | 2022 | 2023 | 2024 | 2025
Revenue — Auto Components | 610 | 630 | 615 | 570 | Ex.3
Revenue — Industrial Equipment & Machinery | 350 | 375 | 400 | 405 | Ex.3
Revenue — Specialty Materials & Coatings | 190 | 200 | 215 | 215 | Ex.3
Total segment revenue | 1150 | 1205 | 1230 | 1190
EBITDA — Auto Components | 68 | 58 | 30 | 5 | Ex.3. Direct project costs charged to segments; shared corporate & central digital costs allocated by revenue
EBITDA — Industrial Equipment & Machinery | 40 | 42 | 38 | 33 | Ex.3
EBITDA — Specialty Materials & Coatings | 14 | 8 | 2 | -13 | Ex.3
Total segment EBITDA | 122 | 108 | 70 | 25
Exhibit 4 — Cash flow and capital expenditure
USD m (outflows negative) | 2022 | 2023 | 2024 | 2025
Net income |  | 11 | -41 | -105
Add D&A |  | 66 | 78 | 90
Increase in operating working capital |  | -9 | -21 | -11 | Ex.4
Operating cash flow after interest and tax |  | 68 | 16 | -26
Maintenance PPE capex |  | -45 | -45 | -45 | Ex.4 — sustains existing operations; case asks to justify any reduction
Physical upgrade and expansion capex |  | -35 | -30 | -25 | Ex.4
Capitalised Factory of the Future spend |  | -50 | -55 | -45 | Ex.4
Other intangible additions |  | -10 | 0 | 0 | Ex.4
Total capital expenditure |  | -140 | -130 | -115
Free cash flow before disposals |  | -72 | -114 | -141
Other intangible disposal proceeds |  | 0 | 19 | 31 | Ex.4 — non-core licences sold at carrying value
Net debt raised |  | 65 | 75 | 85 | Ex.4
Dividends paid |  | -8 | 0 | 0 | Ex.4
Net change in cash |  | -15 | -20 | -25
Opening cash |  | 90 | 75 | 55
Closing cash |  | 75 | 55 | 30
Check: closing cash − balance-sheet cash (should be 0) |  | 0 | 0 | 0
Check: debt raised − change in total debt (should be 0) |  | 0 | 0 | 0
D&A — PPE |  | 40 | 45 | 50 | Ex.4 asset movement reconciliation
D&A — digital & AI assets |  | 15 | 20 | 25 | Ex.4
D&A — other intangibles |  | 11 | 13 | 15 | Ex.4
Check: D&A split − total D&A (should be 0) |  | 0 | 0 | 0

## Case_Digital
Case data — digital programme (Exhibits 5–7, USD m)
Columns: Predictive maintenance (PdM) · Computer-vision inspection (Vision) · Supply-chain planning (SCP) · Programme total.
Exhibit 5 — Programme economics
USD m | PdM | Vision | SCP | Total | Source / note
Capitalised spend 2023–25 | 50 | 55 | 45 | 150 | Ex.5
Net assets at end-2025 | 38 | 44 | 33 | 115 | Ex.5
2025 operating cost (excl. D&A) | 10 | 12 | 14 | 36 | Ex.5
2025 gross benefit (realised, already in Cost of Sales) | 5 | 7 | 1 | 13 | Ex.5 — NOT an exit run-rate; must not be re-counted as future gain
Requested capex, next 18 months (unapproved) | 8 | 12 | 10 | 30 | Ex.5 — excludes recurring opex and remaining implementation
Exhibit 6 — 2025 project operating cost breakdown
USD m | PdM | Vision | SCP | Total
Software and platform licences | 0.8 | 1 | 1.5 | 3.3 | Ex.6 — recurring
Cloud or edge compute and data storage | 0.7 | 1.2 | 1.3 | 3.2 | Ex.6 — recurring
Metered language-model inference / tokens | 0 | 0 | 0.8 | 0.8 | Ex.6 — recurring; planning pilot only (agent calls)
Monitoring, support and model maintenance | 1.5 | 1.8 | 2.4 | 5.7 | Ex.6 — recurring
Recurring operating costs (subtotal) | 3 | 4 | 6 | 13
Systems integration and data engineering | 4 | 4 | 5 | 13 | Ex.6 — temporary
Data preparation, labelling, initial model validation | 2 | 3 | 2 | 7 | Ex.6 — temporary
Training and change management | 1 | 1 | 1 | 3 | Ex.6 — temporary
Temporary implementation costs (subtotal) | 7 | 8 | 8 | 23
Total 2025 project operating cost | 10 | 12 | 14 | 36
Check: Ex.6 total − Ex.5 operating cost (should be 0) | 0 | 0 | 0 | 0
Committed recurring cost payable Jan–Dec 2026 | 1 | 1.5 | 2 | 4.5 | Ex.6 — payable even if deployment stops; included in recurring above
Remaining expensed implementation work in 2026 | 1 | 2 | 3 | 6 | Ex.6 — required to continue CURRENT scope; excludes capex requests
Shared central digital cost (annual) | 12 |  |  |  | Ex.6/Ex.8 — includes payroll of 24-person central team; stays in base case
Central digital team (FTE) | 24 |  |  |  | Ex.8
Exhibit 7 — Deployment and operational evidence (deployed scope only)
| PdM | Vision | SCP
KPI | Unplanned downtime (% sched. hrs) | Scrap/rework (% covered-line cost) | Pilot inventory days |  | Ex.7
Deployed scope (machines / lines / plants) | 150 | 8 | 3 |  | Ex.7 — PdM 150 machines (2 Auto + 1 IEM plant); Vision 8 lines (2 Auto + 1 SMC plant); SCP 3 plants (2 Auto + 1 IEM)
Baseline | 12% | 6% | 90 |  | Ex.7
Original business-case target | 7% | 3.5% | 75 |  | Ex.7 — targets, not achieved results
2025 outcome | 9% | 4.8% | 94 |  | Ex.7
Adoption metric | 60% | 45% | 35% |  | Ex.7 — PdM: actionable alerts closed in window; Vision: flagged rejects needing manual review; SCP: schedules accepted without override
On-time delivery (SCP pilot): baseline / 2025 |  |  | 86% |  | Ex.7 — 86% baseline, 86% in 2025 (no change)
Reported constraint | Maint. records, work-order integration, technicians | Calibration on spec change; selected families only | Master-data inconsistency; separate planning systems |  | Ex.7

## Case_Ops
Case data — operating context (Exhibit 8)
Manufacturing footprint and operating costs (2025)
| Auto | IEM | SMC | Group | Source / note
Plants | 5 | 3 | 3 | 11 | Ex.8 — Auto: India 3, Vietnam 1, CE 1; IEM: India 1, Vietnam 1, CE 1; SMC: India 2, CE 1
Capacity utilisation | 72% | 81% | 67% |  | Ex.8 — actual output / practical capacity at 2025 mix
Energy expenditure (USD m, in Cost of Sales) | 45 | 25 | 50 | 120 | Ex.8
Direct production labour (USD m, in Cost of Sales) | 95 | 60 | 25 | 180 | Ex.8
Main processes | Machining, forging, assembly | Fabrication, machining, assembly | Mixing, batch processing, coating |  | Ex.8
Principal customer requirements | Accuracy, traceability, delivery, price | Reliability, configurability, lead time, service | Batch consistency, performance, tech support |  | Ex.8
Digital readiness
Plants on shared ERP (of 11) | 8 |  |  |  | Ex.8 — 3 plants on local systems with monthly manual consolidation
Production equipment with centrally accessible machine data | 40% |  |  |  | Ex.8 — rest on local logs/manual records; data definitions vary across plants

## Diagnosis
Diagnosis — what the exhibits say
1. Profitability, leverage and liquidity
| 2022 | 2023 | 2024 | 2025 | Reading
Revenue growth |  | 4.783% | 2.075% | -3.252%
Gross margin | 25.22% | 24.48% | 23.17% | 21.85% | Down ~3.4pp despite 13 of digital benefits inside 2025 COGS
EBITDA margin | 10.61% | 8.963% | 5.691% | 2.101%
Opex (excl. D&A) / revenue | 14.61% | 15.52% | 17.48% | 19.75%
Digital & AI opex / revenue | 0.6957% | 1.494% | 2.846% | 4.034% | Digital opex 6x since 2022 (8 → 48)
Total debt (short + long term) | 560 | 625 | 700 | 785
Net debt | 470 | 550 | 645 | 755
Net debt / EBITDA | 3.8525 | 5.0926 | 9.2143 | 30.2 | 30x in 2025 — ratings downgrade warning is unsurprising
Interest cover (EBITDA / net finance costs) | 5.0833 | 4 | 2.1212 | 0.625 | Below 1.0x: operating earnings no longer cover interest
Implied interest rate (finance cost / average debt) |  | 4.557% | 4.981% | 5.387% | 2025 rate used to project interest (Assumptions)
Short-term debt / total debt | 16.07% | 18.4% | 20.71% | 22.93% | Refinancing risk rising: 180 due within 12 months vs 30 cash
2. Working capital
| 2022 | 2023 | 2024 | 2025
Operating working capital | 173 | 182 | 203 | 214 | Ex.4 definition
Check: Δ working capital + cash-flow line (should be 0) |  | 0 | 0 | 0
Inventory days (inventory / COGS × 365) | 87.0058 | 88.2418 | 92.6984 | 100.0806 | 87 → 100 days: ~33 of cash tied up vs 2022 level
Receivable days (DSO) | 47.6087 | 47.8589 | 49.8537 | 52.7563
Payable days (DPO) | 70.0291 | 71.3956 | 72.6138 | 76.5323 | Not used as a lever: stretching suppliers during a downgrade is high-risk
Cash conversion cycle (days) | 64.5854 | 64.7051 | 69.9383 | 76.3047
3. Segment EBITDA margins
| 2022 | 2023 | 2024 | 2025
Auto Components | 11.15% | 9.206% | 4.878% | 0.8772% | 11.1% → 0.9%: in forced-sale territory
Industrial Equipment & Machinery | 11.43% | 11.2% | 9.5% | 8.148% | Growing; the healthiest business
Specialty Materials & Coatings | 7.368% | 4% | 0.9302% | -6.047% | Loss-making; energy is 23% of revenue
4. EBITDA bridge 2022 → 2025
USD m | Impact | % of decline
EBITDA 2022 | 122
Underlying gross-profit erosion (excl. digital benefits) | -43 | 44.33% |  |  | OEM pricing, input & energy costs, mix — the COO and Auto sales head are both right
Digital gross benefits realised in COGS (2025) | 13 | -13.4%
Increase in digital & AI opex | -40 | 41.24% |  |  | Single largest controllable driver
Increase in non-digital personnel | -18 | 18.56%
Increase in selling & customer support | -10 | 10.31%
Change in other overheads | 1 | -1.031%
EBITDA 2025 | 25
Check: bridge end − reported 2025 EBITDA (should be 0) | 0
Memo: segment EBITDA change — Auto | -63 | 64.95% |  |  | Auto explains ~2/3 of the Group decline
Memo: segment EBITDA change — IEM | -7 | 7.216%
Memo: segment EBITDA change — SMC | -27 | 27.84%
5. Factory of the Future scorecard (2025)
USD m | PdM | Vision | SCP | Programme
2025 operating cost | 10 | 12 | 14 | 36
of which recurring | 3 | 4 | 6 | 13
of which temporary implementation | 7 | 8 | 8 | 23
2025 gross benefit | 5 | 7 | 1 | 13
Net 2025 P&L effect (benefit − operating cost) | -5 | -5 | -13 | -23
Net recurring effect (benefit − recurring cost) | 2 | 3 | -5 | 0 | PdM and Vision pay their running costs; SCP does not
Benefit per $ of recurring cost | 1.6667 | 1.75 | 0.16667 | 1
Share of targeted KPI improvement achieved | 60% | 48% | -26.67% |  | PdM 60%, Vision 48%; SCP negative — inventory days rose 90 → 94
Capitalised spend 2023–25 | 50 | 55 | 45 | 150
Years of net recurring benefit to recover capitalised spend | 25 | 18.3333 | never |  | At current scope, even the winners take 18–25 years: scale and adoption are the issue, not the technology
Total digital & AI opex 2025 (projects + central) | 48 |  |  |  | 36 project + 12 shared central
Check: vs Ex.1 digital opex (should be 0) | 0
Net digital P&L 2025 (benefits − all digital opex) | -35 |  |  |  | Digital is currently a −35 drag on a 25 EBITDA business
6. What improves automatically in 2026 (not claimed as our impact)
2025 temporary implementation cost | 23
Remaining implementation work required in 2026 (current scope) | 6
Automatic 2026 EBITDA roll-off vs 2025 | 17 |  |  |  | Temporary costs do not recur (Ex.6). Base case gets this too — our plan must beat it
7. How much of Auto's collapse is digital? (allocation assumption)
Pilot project opex borne by Auto | 24 |  |  |  | Pilots sit in 2 Auto plants of 3 per project → 2/3 share (assumption)
Central digital cost allocated to Auto (by revenue) | 5.7479 |  |  |  | Ex.3 allocation rule
Digital benefits accruing to Auto | 8.6667
Net digital drag on Auto EBITDA | -21.0812
Auto EBITDA excluding net digital drag | 26.0812
Auto EBITDA margin excluding net digital drag | 4.576% |  |  |  | Still far below 11.1% in 2022 → the rest is pricing/volume/input cost: digital must reach commercial & procurement
8. Consistency flag — Vision benefit vs scrap reduction
Implied covered-line production cost (benefit ÷ scrap-point reduction) | 583.3333 |  |  |  | 7.0 ÷ 1.2% ≈ 583
Implied share of Group cost of sales on 8 lines | 62.72% |  |  |  | Implausible for 8 lines → benefit likely includes inspection-labour savings. We do NOT extrapolate this ratio; new lines are haircut 50%

## Assumptions
Assumptions — every judgement call in one place
Blue = our assumption (edit to test). Yellow = key driver. Green = linked from case data. [Bx] codes point to the Sources tab.
Assumption | Unit | Value | Rationale / benchmark
General
Benefit realisation factor (base case) |  | 75% | Pilots achieved 48–60% of targeted KPI gains (Ex.7); benchmark levers are already sized well below published ranges → 75% sits between. 100% = stretch, 50% = downside (Sensitivity). Not applied to F3 (contractual cost removal)
Auto share of pilot project cost & benefit |  | 66.67% | Each pilot runs in 2 Auto plants out of 3 (Ex.7); allocation by plant count
Incremental recurring cost per unit when scaling, vs pilot per-unit cost |  | 67% | Platform licences, monitoring and team are shared, so scaling costs less than the pilot per unit
Interest rate on debt (before refinancing premium) |  | 5.387% | 2025 implied: 40 ÷ average debt of 742 (Diagnosis). Applied to opening debt each period (avoids circularity)
Refinancing premium on rolled-over short-term debt and all new money |  | 3% | Assumption: +300bp for a borrower on downgrade watch; applied from Jan-26 to the 180 of short-term debt and to every dollar of new borrowing
Minimum cash balance |  | 30 | Held at the 2025 closing level; any shortfall is funded by debt
Cash tax |  | 0 | PBT stays negative through Jun-27 in every case (checked on Projection); no cash tax
D&A per year (for PBT check only) |  | 90 | Held at 2025 level; used only to confirm PBT < 0
Steady-state digital capex per year after the mandate |  | 10 | Used only for the run-rate cash break-even test
Revenue and underlying gross margin held at 2025 levels |  | Held | No market recovery and no further erosion assumed. OEM price-down and volume risks shown on Sensitivity
Base case (momentum: current scope continues, capex requests approved as submitted)
Base: upgrade & expansion capex per year |  | 25 | 2025 level (Ex.4)
Base: digital capex over 18 months |  | 30 | All three requests approved (8 + 12 + 10; Ex.5)
Base: share of 18-month digital capex spent in 2026 |  | 66.67% | Straight-line over 18 months
Capex policy (plan)
Maintenance capex per year (plan and base) |  | 45 | NOT reduced: already below PPE depreciation of 50 (Ex.4); case requires justification for any cut
Plan: upgrade & expansion capex per year |  | 10 | Defer expansion: utilisation is 72% Auto, 81% IEM, 67% SMC (Ex.8), so no business is capacity-constrained. Keep 10 for safety/debottlenecking
W1 Foundations
F1 Master data & ERP harmonisation: capex |  | 10 | Redirect the SCP capex request (10) to move the 3 local-system plants onto the shared ERP in waves + master-data tooling
F1: one-off implementation opex |  | 3 | Uses the SCP remaining-work budget (3.0), repurposed to data cleansing and governance
F1: recurring cost (data stewards, MDM tool) |  | 0.5 | Assumption: ~5 data stewards across plants + MDM licence
F2 Digital Value Office: recurring cost |  | 1 | Chief Digital Officer reporting to CEO + 4 business product owners + value tracking; central team of 24 reallocated, not added
F2: one-off change management & training |  | 0.5 | Plant digital-champion network, adoption training
F3 SCP descope: licences retained |  | 100% | Keep the core planning tool so planners keep working and data fixes can be tested
F3: cloud/compute retained |  | 50% | Smaller footprint once agent layer is off
F3: language-model tokens retained |  | 0% | Switch off the agentic layer: 35% acceptance, inventory days worse (Ex.7)
F3: monitoring & model maintenance retained |  | 40% | Fewer models to maintain
F3: one-off transition / shutdown cost |  | 0.5 | Case requires an explicit assumption (Ex.6). 2026 commitments (2.0) are below the retained run-cost (3.1) and lapse without penalty from Jan-27
W2 Maintenance · W3 Quality (fix and scale what works)
S1 PdM current cohort: target downtime by Jun-27 |  | 7.5% | 12% → 7.5% = 37.5% reduction, inside McKinsey's 30–50% range [B1]; short of the 7% business-case target given technician constraints
S1: recurring cost (technician capacity, work-order integration upkeep) |  | 0.5 | Close the loop: alerts closed in window 60% → 85% (month-6 gate)
S2 PdM scale-up: additional connected assets |  | 150 | Doubles the cohort, IEM-led (81% utilisation, growing); released only after the S1 gate
S2: benefit per asset vs pilot |  | 70% | Haircut for new plants and lower data readiness (40% machine-data coverage, Ex.8)
S2: share of new assets in Auto |  | 30% | Rest in IEM
S2: one-off implementation opex |  | 2 | Integration + model tuning for new assets
S2: capex |  | 8 | Approve the PdM request (Ex.5), released in tranches after the gate
S3 Vision current lines: target scrap/rework by Jun-27 |  | 4.2% | 6.0% → 4.2% = 72% of targeted improvement (vs 48% today) via retraining and a calibration workflow for spec changes
S3: one-off retraining / calibration workflow |  | 0.5 | Remaining 2026 work (2.0) is already in the base case
S4 Vision + traceability: additional Auto lines (gated, one named OEM programme) |  | 3 | Only where an OEM programme demands part-level traceability; capex released after month-9 gate. EBITDA-neutral — justified as customer retention, so kept small
S4: benefit per line vs pilot average |  | 50% | Pilot ratio implies implausible covered cost (Diagnosis §8) → 50% haircut
S4: one-off implementation opex |  | 0.8 | Stations, calibration for new part families
S4: capex |  | 4 | Cut the 12 request to 4: three Auto lines for one OEM programme
W4 Energy & process · W5 Procurement · W6 Commercial & back-office · W7 Service growth
N1 Energy management: saving on Auto energy (forging) |  | 6% | Sub-metering + load scheduling + furnace optimisation. ISO 50001 plants ~4.1% in year 1 [B3]; APC up to 10% energy reduction [B2]
N1: saving on IEM energy |  | 3% | Less energy-intensive assembly; lower target
N1: saving on SMC energy |  | 6% | Batch heating/curing: energy is 23% of SMC revenue (Ex.8)
N1: recurring cost (energy platform, analyst) |  | 0.8
N1: one-off implementation opex |  | 1
N1: capex (sub-metering, controls) |  | 3 | Needed: only 40% of equipment has central machine data (Ex.8)
N2 SMC golden-batch / process control: yield gain on SMC materials & other cost |  | 2% | APC delivers up to 5% yield [B2]. Sized on materials only (energy excluded) → no overlap with N1. Funded only if SMC passes the month-6 gate
N2: recurring cost |  | 0.4
N2: one-off implementation opex |  | 0.8
N2: capex (process sensors) |  | 2
N3 Procurement analytics: addressable share of non-energy, non-labour COGS |  | 70% | COGS 930 − energy 120 − labour 180 = 630; ~70% is bought-in materials & parts (assumption)
N3: net saving on addressable spend |  | 1.25% | Far below the 6–12% McKinsey observes in chemicals procurement [B4]
N3: recurring cost (spend-cube tool, 2 analysts) |  | 0.5
N3: one-off implementation opex |  | 1
N4 Commercial: index-linked cost pass-through, Auto |  | 0.5% | NOT a list-price rise: inserts energy/raw-material index clauses at named OEM contract renewals, recovering inflation Ironbridge absorbed. Pricing programmes add 2–7pp ROS [B5]
N4: price realisation, IEM (configure-price-quote) |  | 0.5% | Configuration flexibility is valued (Ex.8); CPQ cuts quote lead time and discount leakage
N4: price realisation, SMC (cost pass-through, specialty value pricing) |  | 1% | SMC EBITDA fell 15 in 2025 on flat revenue → energy/input inflation not passed on. Specialty coatings carry more pricing power than auto parts
N4: recurring cost (pricing analysts, CPQ licence) |  | 0.7 | Covers all three businesses
N4: one-off implementation opex |  | 1
N5 IEM connected-service pilot: service revenue as % of IEM revenue by Jun-27 |  | 1% | Remote monitoring + predictive service on installed pumps/drives, reusing the PdM stack
N5: EBITDA margin on service revenue |  | 20% | Aftermarket services average 25% EBIT vs 10% for new equipment [B6]; haircut for start-up
N5: one-off (offer design, pilot contracts) |  | 1
N5: capex (sensor kits for pilot fleet) |  | 2
N6 Back-office & customer-support automation: addressable cost |  | 153 | Non-digital personnel (108) + selling & customer support (45): up 28 since 2022 while revenue rose 3.5% (Ex.1)
N6: productivity saving on addressable cost |  | 4% | GenAI in customer care: 30–45% of function cost [B8]; automation of the 3 plants' manual month-end consolidation (Ex.8). Delivered via attrition and hiring freeze
N6: recurring cost (GenAI licences, tokens, automation upkeep) |  | 1 | Token spend budgeted explicitly — the SCP lesson (Ex.6)
N6: one-off implementation opex |  | 1
Overlap netting (so benefits are not double-counted)
O2: share of Auto procurement savings passed back to OEMs |  | 50% | Index-linked clauses work both ways: cheaper indexed materials flow through to OEM prices. Applied to Auto's revenue share of N3
O3: share of Auto productivity savings conceded in OEM annual price-downs |  | 25% | Auto OEMs typically ask for annual productivity give-backs; applied to Auto's share of PdM, vision and energy savings
Working capital (plan) — phased after the master-data fix
Inventory days — Dec-26 |  | 96 | From 100. 2026: slow-mover clean-up and safety-stock reset only (does not need the planning tool)
Inventory days — Jun-27 |  | 90 | After F1 master data: 2023 level was 88. A 10% cut vs 30% achieved in a McKinsey SC case [B7]
Receivable days (DSO) — Dec-26 |  | 51 | From 52.8. E-invoicing, collections analytics, dispute resolution
Receivable days (DSO) — Jun-27 |  | 49 | 2023 level was 47.9
Funding bridge (balance-sheet actions, outside the digital numbers)
Further non-core licence disposals |  | 20 | Precedent in the case: non-core licences sold at carrying value — 19 (2024), 31 (2025); 113 of other intangibles remain (Ex.2, Ex.4)
Sale-and-leaseback of selected plant property |  | 40 | Assumption: ~6% of 680 net PPE. Creates a lease liability: buys liquidity, not deleveraging
Supply-chain finance / non-recourse receivables factoring |  | 25 | Assumption: ~15% of 172 receivables, on OEM-backed programmes
Sensitivity inputs
Auto contribution margin (for volume shocks) |  | 25% | Assumption: materials, energy and ~half of direct labour vary with volume
Win condition — what "turned around by Jun-27" means (tests a board and its lenders would apply)
Liquidity: new money needed beyond rolling the 180 and identified sources — at most |  | 0 | The company can fund the mandate without asking lenders for fresh money (2025: FCF −141)
Solvency: exit run-rate interest cover in the DOWNSIDE case (50% realisation) — at least |  | 1 | Earnings cover interest again even if only half the benefits land (2025: 0.6x)
Auto plants' share of maintenance capex (5 of 11 plants) |  | 20.4545 | Proxy for the capex Auto needs to stand still; allocation by plant count (assumption)
Digital: net digital contribution at Jun-27 run-rate — above |  | 0 | Digital pays for itself (2025: −35)

## Initiatives
Initiatives — run-rate economics, phasing, workstreams and segment split
Part A derives each lever's annual run-rate at June 2027 from Assumptions. Part B applies the realisation factor and phases it over the mandate. Ramps are % of annual run-rate achieved on average in the period.
Part A — Run-rate derivation (USD m, annual at Jun-27, before realisation factor)
Initiative | Workstream | Gross benefit | Recurring cost | One-off opex (18m) | Capex (18m) | Revenue added | Realisation applies (1/0) | [16 empty] | How the benefit is calculated
F1 · Master data & ERP harmonisation (3 plants, in waves) | W1 Foundations | 0 | 0.5 | 3 | 10 | 0 | 1 | [16 empty] | Enabler: unlocks the 2027 inventory release, procurement analytics and any later planning automation
F2 · Digital Value Office & Chief Digital Officer | W1 Foundations | 0 | 1 | 0.5 | 0 | 0 | 1 | [16 empty] | Enabler: business-owned use cases, numeric stage-gates, value tracking
F3 · Switch off SCP agentic layer; keep core planning tool | W1 Foundations | 2.89 | 0 | -2.5 | 0 | 0 | 0 | [16 empty] | Avoided SCP recurring cost (contractual, so no realisation haircut). One-off negative: remaining SCP work (3.0) avoided, net of 0.5 transition
S1 · PdM: close the loop on current 150 machines | W2 Maintenance | 2.5 | 0.5 | 0 | 0 | 0 | 1 | [16 empty] | Pilot benefit per downtime point (5.0 ÷ 3pt) × further points (9.0% → 7.5%)
S2 · PdM: scale to +150 assets (IEM-led, gated) | W2 Maintenance | 3.5 | 2.01 | 2 | 8 | 0 | 1 | [16 empty] | Pilot benefit per machine (5.0 ÷ 150) × assets × 70%; cost per machine (3.0 ÷ 150) × 67%
S3 · Vision: retrain & calibrate current 8 lines | W3 Quality | 3.5 | 0 | 0.5 | 0 | 0 | 1 | [16 empty] | Pilot benefit per scrap point on the SAME lines (7.0 ÷ 1.2pt) × further points (4.8% → 4.2%)
S4 · Vision + traceability: +3 Auto lines (gated) | W3 Quality | 1.3125 | 1.005 | 0.8 | 4 | 0 | 1 | [16 empty] | Pilot benefit per line (7.0 ÷ 8) × 50% haircut; cost per line (4.0 ÷ 8) × 67%. Justified mainly by OEM traceability
N1 · Energy management & optimisation | W4 Energy & process | 6.45 | 0.8 | 1 | 3 | 0 | 1 | [16 empty] | Segment energy spend (Ex.8) × saving %
N2 · SMC golden-batch & process control (gated) | W4 Energy & process | 1.8605 | 0.4 | 0.8 | 2 | 0 | 1 | [16 empty] | SMC COGS proxied at Group COGS/revenue ratio, less SMC energy & labour → materials ≈ 93; × 2% yield
N3 · Procurement spend analytics & should-cost | W5 Procurement | 5.5125 | 0.5 | 1 | 0 | 0 | 1 | [16 empty] | (930 − 120 − 180) × 70% addressable × 1.25%
N4 · Cost pass-through & quoting (index clauses, CPQ) | W6 Commercial & back-office | 7.025 | 0.7 | 1 | 0 | 7.025 | 1 | [16 empty] | Segment revenue × price realisation (Auto 0.5%, IEM 0.5%, SMC 1.0%)
N6 · Back-office & customer-support automation | W6 Commercial & back-office | 6.12 | 1 | 1 | 0 | 0 | 1 | [16 empty] | (108 personnel + 45 selling & support) × 4%
N5 · IEM connected-service pilot ("predictive service") | W7 Service growth | 0.81 | 0 | 1 | 2 | 4.05 | 1 | [16 empty] | IEM revenue × 1% service revenue × 20% margin — a growth option more than a 2027 profit driver
O2 · Less: procurement savings passed to OEMs | Overlap netting | -1.3202 | 0 | 0 | 0 | 0 | 1 | [16 empty] | Index-linked contracts hand back part of Auto's share of N3
O3 · Less: OEM productivity give-backs | Overlap netting | -2.2656 | 0 | 0 | 0 | 0 | 1 | [16 empty] | Share of Auto's PdM, vision and energy savings conceded in annual price-downs
Total |  | 37.8947 | 8.415 | 10.1 | 29 | 11.075
of which gross benefit subject to realisation |  | 35.0047
of which gross benefit not subject to realisation |  | 2.89
Part B — Phasing over the mandate (Jan-26 to Jun-27) and segment split — after realisation factor
Initiative | Workstream | Benefit RR | Cost RR | Net RR | Ben. ramp 2026 | Ben. ramp H1-27 | Cost ramp 2026 | Cost ramp H1-27 | One-off 18m | One-off % 2026 | Capex 18m | Capex % 2026 | EBITDA 2026 | EBITDA H1-27 | EBITDA 18m | Capex 2026 | Capex H1-27 | Feasibility (1–5) | Months to value | Auto | IEM | SMC | Split check | Phasing rationale
F1 · Master data & ERP harmonisation (3 plants, in waves) | W1 Foundations | 0 | 0.5 | -0.5 | 0% | 0% | 40% | 100% | 3 | 60% | 10 | 60% | -2 | -1.45 | -3.45 | 6 | 4 | 3 | 9 | 47.9% | 34.03% | 18.07% | 100% | ERP cut-over in waves, months 4–16; no P&L inside the window — the base for 2027+
F2 · Digital Value Office & Chief Digital Officer | W1 Foundations | 0 | 1 | -1 | 0% | 0% | 90% | 100% | 0.5 | 70% | 0 | 0% | -1.25 | -0.65 | -1.9 | 0 | 0 | 5 | 1 | 47.9% | 34.03% | 18.07% | 100% | Stood up in month 1
F3 · Switch off SCP agentic layer; keep core planning tool | W1 Foundations | 2.89 | 0 | 2.89 | 75% | 100% | 0% | 0% | -2.5 | 100% | 0 | 0% | 4.6675 | 1.445 | 6.1125 | 0 | 0 | 5 | 3 | 66.67% | 33.33% | 0% | 100% | Agent layer off from April 2026 after Q1 contract review
S1 · PdM: close the loop on current 150 machines | W2 Maintenance | 1.875 | 0.5 | 1.375 | 50% | 100% | 75% | 100% | 0 | 100% | 0 | 0% | 0.5625 | 0.6875 | 1.25 | 0 | 0 | 4 | 4 | 66.67% | 33.33% | 0% | 100% | Work-order integration is the remaining 2026 scope; month-6 gate: ≥85% alerts closed on time
S2 · PdM: scale to +150 assets (IEM-led, gated) | W2 Maintenance | 2.625 | 2.01 | 0.615 | 20% | 75% | 40% | 100% | 2 | 60% | 8 | 60% | -1.479 | -0.82063 | -2.2996 | 4.8 | 3.2 | 3 | 9 | 30% | 70% | 0% | 100% | Capex released only after the S1 gate is met
S3 · Vision: retrain & calibrate current 8 lines | W3 Quality | 2.625 | 0 | 2.625 | 50% | 100% | 0% | 0% | 0.5 | 100% | 0 | 0% | 0.8125 | 1.3125 | 2.125 | 0 | 0 | 4 | 4 | 66.67% | 0% | 33.33% | 100% | Retraining in H1-26; month-6 gate: manual review ≤25% of flagged rejects
S4 · Vision + traceability: +3 Auto lines (gated) | W3 Quality | 0.98438 | 1.005 | -0.020625 | 0% | 40% | 10% | 80% | 0.8 | 30% | 4 | 25% | -0.3405 | -0.76513 | -1.1056 | 1 | 3 | 3 | 12 | 100% | 0% | 0% | 100% | Month-9 gate: S3 gate met AND named OEM programme requires traceability
N1 · Energy management & optimisation | W4 Energy & process | 4.8375 | 0.8 | 4.0375 | 40% | 85% | 60% | 100% | 1 | 70% | 3 | 80% | 0.755 | 1.3559 | 2.1109 | 2.4 | 0.6 | 4 | 6 | 41.86% | 11.63% | 46.51% | 100% | Metering first, then scheduling and set-point optimisation — starts month 1
N2 · SMC golden-batch & process control (gated) | W4 Energy & process | 1.3954 | 0.4 | 0.99538 | 10% | 60% | 30% | 100% | 0.8 | 50% | 2 | 50% | -0.38046 | -0.18139 | -0.56185 | 1 | 1 | 2 | 12 | 0% | 0% | 100% | 100% | Funded only if SMC passes the month-6 fix-or-exit gate
N3 · Procurement spend analytics & should-cost | W5 Procurement | 4.1344 | 0.5 | 3.6344 | 50% | 90% | 70% | 100% | 1 | 80% | 0 | 0% | 0.91719 | 1.4105 | 2.3277 | 0 | 0 | 4 | 4 | 47.9% | 34.03% | 18.07% | 100% | No-capex quick win: spend cube from AP data starts month 1
N4 · Cost pass-through & quoting (index clauses, CPQ) | W6 Commercial & back-office | 5.2687 | 0.7 | 4.5687 | 40% | 85% | 70% | 100% | 1 | 80% | 0 | 0% | 0.8175 | 1.6892 | 2.5067 | 0 | 0 | 3 | 6 | 40.57% | 28.83% | 30.6% | 100% | Index clauses land at each OEM contract renewal; SMC/IEM quoting from month 2
N6 · Back-office & customer-support automation | W6 Commercial & back-office | 4.59 | 1 | 3.59 | 25% | 70% | 60% | 100% | 1 | 70% | 0 | 0% | -0.1525 | 0.8065 | 0.654 | 0 | 0 | 4 | 6 | 47.9% | 34.03% | 18.07% | 100% | Customer-support copilot and consolidation automation; savings via attrition
N5 · IEM connected-service pilot ("predictive service") | W7 Service growth | 0.6075 | 0 | 0.6075 | 10% | 50% | 0% | 0% | 1 | 60% | 2 | 60% | -0.53925 | -0.24813 | -0.78738 | 1.2 | 0.8 | 2 | 12 | 0% | 100% | 0% | 100% | Pilot contracts signed H2-26; revenue in 2027
O2 · Less: procurement savings passed to OEMs | Overlap netting | -0.99017 | 0 | -0.99017 | 50% | 90% | 0% | 0% | 0 | 0% | 0 | 0% | -0.49508 | -0.44557 | -0.94066 | 0 | 0 |  |  | 100% | 0% | 0% | 100% | Follows N3 phasing
O3 · Less: OEM productivity give-backs | Overlap netting | -1.6992 | 0 | -1.6992 | 35% | 80% | 0% | 0% | 0 | 0% | 0 | 0% | -0.59473 | -0.67969 | -1.2744 | 0 | 0 |  |  | 100% | 0% | 0% | 100% | Follows PdM/vision/energy phasing
Total |  | 29.1435 | 8.415 | 20.7285 |  |  |  |  | 10.1 |  | 29 |  | 1.3007 | 3.4666 | 4.7673 | 16.4 | 12.6
Part C — Workstream view (what the deck shows)
Workstream |  | Net RR | EBITDA 2026 | EBITDA H1-27 | EBITDA 18m | One-off 18m | Capex 18m
W1 Foundations |  | 1.39 | 1.4175 | -0.655 | 0.7625 | 1 | 10
W2 Maintenance |  | 1.99 | -0.9165 | -0.13312 | -1.0496 | 2 | 8
W3 Quality |  | 2.6044 | 0.472 | 0.54737 | 1.0194 | 1.3 | 4
W4 Energy & process |  | 5.0329 | 0.37454 | 1.1746 | 1.5491 | 1.8 | 5
W5 Procurement |  | 3.6344 | 0.91719 | 1.4105 | 2.3277 | 1 | 0
W6 Commercial & back-office |  | 8.1587 | 0.665 | 2.4957 | 3.1607 | 2 | 0
W7 Service growth |  | 0.6075 | -0.53925 | -0.24813 | -0.78738 | 1 | 2
Overlap netting |  | -2.6894 | -1.0898 | -1.1253 | -2.2151 | 0 | 0
Total |  | 20.7285 | 1.3007 | 3.4666 | 4.7673 | 10.1 | 29
Check: workstream total − initiative total (should be 0) |  | 0
Part D — Working-capital release (cash only; separate from recurring EBITDA as the case requires)
USD m |  | 2025A | Dec-26 | Jun-27
Inventory days |  | 100.0806 | 96 | 90
Inventory balance (at 2025 COGS) |  | 255 | 244.6027 | 229.3151
Inventory release in period |  |  | 10.3973 | 15.2877
Receivable days |  | 52.7563 | 51 | 49
Receivables balance (at 2025 revenue) |  | 172 | 166.274 | 159.7534
Receivables release in period |  |  | 5.726 | 6.5205
Total working-capital release |  |  | 16.1233 | 21.8082 | [19 empty] | One-off cash, not EBITDA

## Projection
Projection — base (momentum) vs plan, Jan-2026 to Jun-2027
Base = current digital scope continues and all capex requests are approved; no new initiatives. Plan = this strategy at the base-case realisation factor. RR columns annualise the June-2027 exit position.
USD m | 2025A | 2026 Base | H1-27 Base | 18m Base | 2026 Plan | H1-27 Plan | 18m Plan | Jun-27 RR Base | Jun-27 RR Plan | Note
EBITDA
EBITDA 2025 (starting point) | 25 | 25 | 12.5 | 37.5 | 25 | 12.5 | 37.5 | 25 | 25 | Revenue and underlying margin held at 2025 (Assumptions)
One-off 2025 implementation costs rolling off (Ex.6) |  | 17 | 11.5 | 28.5 | 17 | 11.5 | 28.5 | 23 | 23 | 23 of 2025 temporary costs do not recur; 6 of remaining work falls in 2026. Happens in both cases — not claimed
Initiatives, net of costs (at realisation factor) |  | 0 | 0 | 0 | 1.3007 | 3.4666 | 4.7673 | 0 | 20.7285 | Initiatives Part B
EBITDA | 25 | 42 | 24 | 66 | 43.3007 | 27.4666 | 70.7673 | 48 | 68.7285
Revenue (run-rate) | 1190 | [6 empty] | 1190 | 1198.3063 | Plan adds price realisation (N4) and service revenue (N5)
EBITDA margin (run-rate) | 2.101% | [6 empty] | 4.034% | 5.735%
Cash flow
Interest at 2025 rate on opening debt | -40 | -42.2896 | -23.6496 | -65.9391 | -42.2896 | -22.6792 | -64.9688 | -49.9251 | -46.2774 | Implied 2025 rate × opening debt of each period
Refinancing premium (short-term debt rolled + new money) | 0 | -2.7 | -4.0948 | -6.7948 | -2.7 | -3.5545 | -6.2545 | -9.652 | -7.6207 | 180 matures through 2026 (rolled evenly → half-year of premium in 2026), fully repriced from 2027; new money priced the same
Net finance costs | -40 | -44.9896 | -27.7444 | -72.734 | -44.9896 | -26.2337 | -71.2233 | -59.5771 | -53.8981
Cash tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Losses: PBT check below
Working-capital release (+) / build (−) | -11 | 0 | 0 | 0 | 16.1233 | 21.8082 | 37.9315 |  |  | Base: days held flat. Plan: Initiatives Part D
Operating cash flow after interest and tax | -26 | -2.9896 | -3.7444 | -6.734 | 14.4344 | 23.0411 | 37.4755
Maintenance capex | -45 | -45 | -22.5 | -67.5 | -45 | -22.5 | -67.5 |  |  | Held at 45/yr in both cases
Upgrade & expansion capex | -25 | -25 | -12.5 | -37.5 | -10 | -5 | -15 |  |  | Plan defers expansion: no segment is capacity-constrained
Digital capex | -45 | -20 | -10 | -30 | -16.4 | -12.6 | -29 |  |  | Base: 30 requested. Plan: re-prioritised, stage-gated portfolio
Total capex | -115 | -90 | -45 | -135 | -71.4 | -40.1 | -111.5
Free cash flow (before disposals and financing) | -141 | -92.9896 | -48.7444 | -141.734 | -56.9656 | -17.0589 | -74.0245
Balance sheet (all shortfalls funded with debt; funding bridge shown below)
Debt raised (+) / repaid (−) to hold minimum cash |  | 92.9896 | 48.7444 | 141.734 | 56.9656 | 17.0589 | 74.0245
Closing cash | 30 | 30 | 30 | 30 | 30 | 30 | 30
Closing debt | 785 | 877.9896 | 926.734 | 926.734 | 841.9656 | 859.0245 | 859.0245
Net debt | 755 | 847.9896 | 896.734 | 896.734 | 811.9656 | 829.0245 | 829.0245 | 896.734 | 829.0245
Credit metrics (period / run-rate)
Net debt / EBITDA (run-rate at period end) | 30.2 | 20.1902 | 18.682 | 18.682 | 18.7518 | 12.0623 | 12.0623 | 18.682 | 12.0623
Interest cover (EBITDA / finance costs) | 0.625 | 0.93355 | 0.86504 | 0.90742 | 0.96246 | 1.047 | 0.9936 | 0.80568 | 1.2752
Check: PBT ≈ EBITDA − D&A − interest (must be < 0 for zero tax) |  | -92.9896 | -48.7444 |  | -91.6889 | -43.7671 |  | -101.5771 | -75.1697
Lender view at Jun-27 — last twelve months (LTM) vs run-rate
| Base | Plan | Δ | [6 empty] | Note
LTM EBITDA (≈ half of 2026 + H1-27) | 45 | 49.1169 | 4.1169 | [6 empty] | Conservative for the plan: in a ramp, H2-26 > H1-26
LTM net finance costs | 50.2392 | 48.7285 | -1.5107
LTM interest cover | 0.89572 | 1.008 | 0.11226 | [6 empty] | What lenders test at the refinancing
Net debt at Jun-27 | 896.734 | 829.0245 | -67.7095
Net debt / LTM EBITDA | 19.9274 | 16.8786 | -3.0488
Run-rate EBITDA at Jun-27 | 48 | 68.7285 | 20.7285
Run-rate interest cover | 0.80568 | 1.2752 | 0.46948
Net debt / run-rate EBITDA | 18.682 | 12.0623 | -6.6196
EBITDA needed for free-cash-flow break-even at run-rate | 139.5771 | 118.8981 | -20.6789 | [6 empty] | Interest + maintenance + expansion + steady-state digital capex
Run-rate EBITDA minus break-even EBITDA | -91.5771 | -50.1697 | 41.4074 | [6 empty] | Negative = debt still grows after Jun-27 → balance-sheet action is required, digital alone cannot stop it
Sources & uses of cash, Jan-26 to Jun-27 (funding bridge)
USD m | Base | Plan | Δ | [6 empty] | Note
Use: free-cash-flow deficit | 141.734 | 74.0245 | -67.7095
Use: short-term debt falling due | 180 | 180 | 0
Total uses | 321.734 | 254.0245 | -67.7095
Source: roll over short-term debt (at premium) | 180 | 180 | 0 | [6 empty] | Requires lenders to believe the plan: LTM cover above 1.0x
Source: further non-core licence disposals | 20 | 20 | 0
Source: sale-and-leaseback | 40 | 40 | 0
Source: supply-chain finance / factoring | 25 | 25 | 0
Source: new term debt / revolving credit (balancing) | 56.734 | -10.9755 | -67.7095 | [6 empty] | Genuinely new money the CEO must raise
Total sources | 321.734 | 254.0245 | -67.7095
Headlines (plan vs base)
Value
Run-rate EBITDA uplift at Jun-27 vs base | 20.7285
18-month free cash flow improvement vs base | 67.7095
Net debt at Jun-27: plan minus base | -67.7095
Net-debt build over 18 months: plan as % of base | 52.23%
Digital & analytics benefits, Jun-27 RR (2025 realised + new, excl. F3) | 39.2535
Digital & AI opex, Jun-27 RR (recurring + central + new − F3 saving) | 30.525
Net digital contribution, Jun-27 RR (2025: −35) | 8.7285

## Segments
Segments — June-2027 run-rate by business (USD m)
Answers "where is a Group-wide approach right and where not?" and whether Auto moves out of forced-sale territory.
| Auto | IEM | SMC | Group | Note
Revenue 2025 | 570 | 405 | 215 | 1190
EBITDA 2025 | 5 | 33 | -13 | 25
EBITDA margin 2025 | 0.8772% | 8.148% | -6.047% | 2.101%
One-off implementation costs rolling off | 15.3333 | 5 | 2.6667 | 23 | PdM & SCP third plant is IEM; Vision third plant is SMC (Ex.7)
Initiatives, net run-rate (incl. overlap netting) | 8.3534 | 6.1943 | 6.1808 | 20.7285 | Net run-rate × segment split (Initiatives Part B)
EBITDA — Jun-27 run-rate | 28.6867 | 44.1943 | -4.1525 | 68.7285
Check: Group vs Projection run-rate (should be 0) |  |  |  | 0
Revenue — Jun-27 run-rate | 572.1375 | 409.5562 | 216.6125 | 1198.3063
EBITDA margin — Jun-27 run-rate | 5.014% | 10.79% | -1.917% | 5.735% | Auto profitable again but below its own 11.1% (2022). Supplier benchmarks are mostly EBIT (after D&A): compare like-for-like
Margin change (pp) | 4.137% | 2.643% | 4.129% | 3.635%
Capacity utilisation 2025 (context) | 72% | 81% | 67% |  | Auto & SMC are demand-constrained: downtime reduction saves cost there, adds throughput only in IEM
SMC price realisation needed for break-even (vs 1.0% assumed) |  |  | 3.575% |  | The month-6 fix-or-exit test
SMC exit case (run-rate EBITDA effect only)
SMC run-rate EBITDA removed |  |  |  | 4.1525
Stranded central digital & foundation costs left with the Group |  |  |  | -2.4391 | Excludes undisclosed corporate overhead allocated to SMC → understates the stranded cost
Change in Group run-rate EBITDA from exiting SMC |  |  |  | 1.7135 | Close to zero: exit is not an EBITDA fix; its value is cash (working capital, capex) and management focus. Loss-making unit → minimal proceeds

## Sensitivity
Sensitivity — how robust is the Jun-27 position?
1. Benefit realisation (initiative benefits scaled, except contractual F3; costs unchanged)
| Downside | Base | Stretch | Upside | Note
Benefit realisation | 50% | 75% | 100% | 125%
Jun-27 run-rate EBITDA | 59.9773 | 68.7285 | 77.4797 | 86.2308 | Momentum run-rate + benefits × factor − recurring costs
EBITDA margin | 5.04% | 5.776% | 6.511% | 7.246%
Net debt / run-rate EBITDA (net debt at base-case plan) | 13.8223 | 12.0623 | 10.6999 | 9.614 | Approximation: holds Jun-27 net debt at the base-case plan value
Run-rate interest cover | 1.1128 | 1.2752 | 1.4375 | 1.5999
Realisation needed for run-rate interest cover of 1.5x | 109.6%
Realisation needed for run-rate interest cover of 2.0x | 186.6% |  |  |  | Above 100% → 2.0x needs balance-sheet action, not more digital
2. One-at-a-time shocks to Jun-27 run-rate EBITDA (base-case plan)
| Shock | Δ EBITDA | EBITDA after | Cover after | Note
Auto OEM price-down not recovered | 1% | -5.7 | 63.0285 | 1.1694 | Each 1% ≈ 5.7 — why index-linked pass-through (N4) matters
Auto OEM volume loss | 5% | -7.125 | 61.6035 | 1.143 | At 25% contribution margin; utilisation would fall further below 72%
Energy price increase | 10% | -12 | 56.7285 | 1.0525 | Energy is 120 of COGS; N1 metering and N4 index clauses partly hedge
PdM & vision scale-ups stopped at their gates | 100% | -0.59437 | 68.1341 | 1.2641 | Small: gates cap the downside
Procurement & pass-through deliver only this share | 50% | -4.2065 | 64.522 | 1.1971 | Net of the O2 overlap
Exit SMC | exit | 1.7135 | 70.442 | 1.3069 | From Segments: near-neutral on EBITDA
Refinancing premium +200bp higher than assumed | 2% |  |  | 1.1653 | Interest, not EBITDA: applied to the 180 + new money

## Sources
Sources — external benchmarks (verified 30 Sep 2026)
Case data is authoritative; benchmarks are used only to size assumptions where the case is silent.
ID | Benchmark (quoted from source) | Source | Used for | URL | Accessed
B1 | Predictive maintenance typically reduces machine downtime by 30–50% and increases machine life by 20–40% | McKinsey & Company, "Manufacturing: Analytics unleashes productivity and profitability", 14 Aug 2017 | S1, S2 downtime target | https://www.mckinsey.com/capabilities/operations/our-insights/manufacturing-analytics-unleashes-productivity-and-profitability | 30-Sep-26
B2 | Optimised advanced process controls: up to 15% more throughput, 5% more yield, 10% less energy | McKinsey & Company, "The potential of advanced process controls in energy and materials", 23 Nov 2020 | N1 energy, N2 yield | https://www.mckinsey.com/industries/metals-and-mining/our-insights/the-potential-of-advanced-process-controls-in-energy-and-materials | 30-Sep-26
B3 | ISO 50001-certified facilities achieve ~4.1% annual energy-performance improvement in the first year and ~3.4% after twelve years | Fitzgerald, Therkelsen, Sheaffer, Rao (Lawrence Berkeley National Laboratory), "Deeper and persistent energy savings and CO2 reductions achieved through ISO 50001 in the manufacturing sector", 2023 | N1 energy | https://smartersmallbuildings.lbl.gov/publications/deeper-and-persistent-energy-savings | 30-Sep-26
B4 | Reducing overall spending by 6–12% is a realistic goal in chemicals procurement | McKinsey & Company, "Technology-enabled procurement for chemical companies", 1 Oct 2019 | N3 procurement | https://www.mckinsey.com/industries/chemicals/our-insights/technology-enabled-procurement-for-chemical-companies | 30-Sep-26
B5 | Across 1,000+ pricing-excellence initiatives, return on sales typically rises 2–7 percentage points | McKinsey & Company, "Turning pricing power into profit", 1 Mar 2015 | N4 commercial | https://www.mckinsey.com/capabilities/growth-marketing-and-sales/our-insights/turning-pricing-power-into-profit | 30-Sep-26
B6 | Average EBIT margin for aftermarket services 25% vs 10% for new equipment (30 industries) | McKinsey & Company, "Industrial aftermarket services: Growing the core", 27 Jul 2017 | N5 service margin | https://www.mckinsey.com/industries/industrials/our-insights/industrial-aftermarket-services-growing-the-core | 30-Sep-26
B7 | Diagnosed ~20% inventory-reduction opportunity; achieved 30% reduction with OTIF rising to 95% | McKinsey & Company, "Supply Chain 4.0: Opportunities to use your supply chain for differentiation", 24 May 2019 | Inventory days target | https://www.mckinsey.com/capabilities/operations/our-insights/operations-blog/supply-chain-40-opportunities-to-use-your-supply-chain-for-differentiation | 30-Sep-26
B8 | Generative AI applied to customer care could increase productivity by 30–45% of current function costs | McKinsey & Company, "The economic potential of generative AI: The next productivity frontier", 14 Jun 2023 | N6 back-office & support automation | https://www.mckinsey.com/capabilities/mckinsey-digital/our-insights/the-economic-potential-of-generative-ai-the-next-productivity-frontier | 30-Sep-26